Assignment 11

Aim : To convert a given discussion into structured meeting minutes using an AI tool, including the agenda, summary, and tasks.

AI Tool Used : ChatGPT

Step 1: Given Discussion

The team discussed plans for an upcoming Artificial Intelligence workshop. The workshop is proposed for 15th November. The coordinator will confirm the guest speaker and seminar hall by 8th November. The student representative will collect the names of interested students by 10th November. A poster and announcement also need to be prepared. The student representative will prepare the poster, while the coordinator will review and approve it. All workshop arrangements should be completed by 12th November.

Step 2: Prompt Used

Convert the following discussion into structured meeting minutes. Include a suitable agenda, a brief summary of the discussion, and a list of tasks with the responsible person and deadline. Use clear headings and bullet points.

Step 3: AI-Generated Structured Meeting Minutes

Meeting Title

Artificial Intelligence Workshop Planning Meeting

Agenda

- Plan the upcoming AI workshop.

- Confirm the workshop date, venue, and guest speaker.

- Prepare the student participant list.

- Create and approve the workshop poster and announcement.

- Finalize all workshop arrangements.

Meeting Summary

The team discussed the arrangements for an upcoming Artificial Intelligence workshop. The proposed date for the workshop is 15th November. The coordinator will confirm the guest speaker and seminar hall. The student representative will collect the names of interested students and prepare the workshop poster. The coordinator will review and approve the poster. All arrangements should be completed by 12th November.

Tasks / Action Items

| Task | Responsible Person | Deadline |
| --- | --- | --- |
| Confirm guest speaker | Coordinator | 8th November |
| Confirm seminar hall | Coordinator | 8th November |
| Collect names of interested students | Student Representative | 10th November |
| Prepare workshop poster | Student Representative | Before 12th November |
| Review and approve poster | Coordinator | Before 12th November |
| Finalize all workshop arrangements | Coordinator / Team | 12th November |

Key Decisions

- The proposed workshop date is 15th November.

- The guest speaker and seminar hall must be confirmed by 8th November.

- All workshop preparations must be completed by 12th November.

Result

The given discussion was successfully converted into structured meeting minutes using an AI tool, including the agenda, meeting summary, key decisions, and clearly assigned tasks with deadlines.