Assignment - 10

Aim : To use a sample meeting conversation and generate meeting notes using an AI tool by identifying the key points and action items.

AI Tool Used : ChatGPT

Step 1: Sample Meeting Conversation

Manager: We need to organize an Artificial Intelligence workshop for students next month.

Coordinator: I suggest conducting the workshop on 15th November. We also need to confirm the seminar hall and invite a guest speaker.

Student Representative: I will collect the names of interested students and prepare the participant list.

Manager: Good. Please complete the participant list by 10th November.

Coordinator: I will contact the guest speaker and confirm the seminar hall by 8th November.

Manager: We also need a poster and announcement for the workshop.

Student Representative: I can prepare the poster and share it with the coordinator for approval.

Manager: Good. Let's finalize all arrangements by 12th November.

Step 2: Prompt Used

Convert the following meeting conversation into clear meeting notes. Identify the main discussion points and action items. For each action item, mention the responsible person and deadline where available. Use a structured format with headings and bullet points.

Step 3: AI-Generated Meeting Notes

Meeting Title

Artificial Intelligence Workshop Planning Meeting

Key Points Discussed

- An AI workshop will be organized for students next month.

- The proposed workshop date is 15th November.

- A seminar hall needs to be confirmed.

- A guest speaker needs to be invited.

- A list of interested students needs to be prepared.

- A poster and announcement need to be created.

- All workshop arrangements should be finalized by 12th November.

Action Items

| Action Item | Responsible Person | Deadline |
| --- | --- | --- |
| Confirm guest speaker | Coordinator | 8th November |
| Confirm seminar hall | Coordinator | 8th November |
| Prepare student participant list | Student Representative | 10th November |
| Prepare workshop poster | Student Representative | Before 12th November |
| Review and approve poster | Coordinator | Before 12th November |
| Finalize all workshop arrangements | Manager | 12th November |

Conclusion

The team agreed to organize an Artificial Intelligence workshop on 15th November. The coordinator will handle the guest speaker and venue, while the student representative will prepare the participant list and poster. All arrangements must be completed by 12th November.

Result

The sample meeting conversation was successfully processed using an AI tool. The important discussion points were identified and converted into structured meeting notes with clear action items, responsible persons, and deadlines.